## User Stories
User Stories - CS 692
Overall Project estimates
| Work estimate for sprint 1 (hrs) | 60
| Work estimate for sprint 2 (hrs) | 60
| Work estimate for sprint 3 (hrs) | 60
| Work estimate for sprint 4 (hrs) | 60
Sprint Information
| Current sprint | 4
| Total available days for the sprint | 21
| Resources available | 5
Story Number | Sprint | User role | User story | Details | Tasks
1 | 1 | Developer | Chatbot functionality | Trained chatbot on more databases so as to provide more information | Train chatbot on nlp databases
2 | 1 | Developer | News Storage in database | Stored static news articles in database | Store static news content in database
3 | 1 | Developer | UI Pages development | Improve the overall UI of the web application | Redesigned the login page & homepage
4 | 1 | Developer | Sprint 1 Presentation | Creating the presentation for sprint 1 | 1. Prepared for sprint 1 presentation 2. Checked all the completed tasks of sprint 1 3. Summarize all the sprint 1 completed task
5 | 2 | Developer | Chatbot functionality | Change chatbot backend | Change chatbot business logic and connect to front end
6 | 2 | Developer | UI Pages development | Dynamic page and content | Add dynamic content - news from RSS feeds
7 | 2 | Developer | Login/Signup Page added | Add user registration, login form | Add user registration/login form, connect to backend database
8 | 2 | Developer | Sprint 2 Presentation | Creating the presentation for sprint 2 | Create presentation slides, add user stories status
9 | 3 | Developer | UI Pages development | Improve homepage UI | Rework UI
10 | 3 | Developer | Chatbot UI | Add chatbot widget | Add chatbot widget and connect to chatbot backend
11 | 3 | Developer | Change chatbot backend | Improve chatbot functionality | Improve chatbot business logic
12 | 3 | Developer | Add News source | Add functionality to fetch latest news | Fetch and display news content from NewsAPI.org
13 | 3 | Developer | Chatbot Custom Actions | Train chatbot to respond based on user query | Code function for chatbot to fetch and provide user requested content
14 | 3 | Developer | Sprint 3 Presentation | Creating the presentation for sprint 3 | Create presentation slides, add user stories status
15 | 4 | Developer | Deploy application to cloud | Deploy project to heroku cloud | Upload project files, database to heroku
16 | 4 | Developer | Improve Chatbot training | Train chatbot to respond based on user searchquery | Code function for chatbot to fetch and provide user topic
17 | 4 | Developer | Sprint 4 Presentation | Creating the presentation for sprint 4 | Create presentation slides, add user stories status