## Sheet 1 - Product Backlog
Product Backlog
Overall Project estimates
| Work estimate for sprint 1 (hrs) | 80
| Work estimate for sprint 2 (hrs) | 80
| Work estimate for sprint 3 (hrs) | 80
| Work estimate for sprint 4 (hrs) | 80
Sprint Information
| Current sprint | 1
| Total available days for the sprint | 10
| Resources available | 5
Application | Sprint | User role | User story | Details | Tasks
NewsAssistant | 1 | Developer | Chatbot functionality | Add funcitionality to chatbot so that it can train itself and provide more information
NewsAssistant | 1 | Developer | UI Pages development | Improve the overall UI of the web application | 1. Redesigned the login page & homepage
NewsAssistant | 1 | Developer | Sprint 1 Presentation | Creating the presentation for sprint 1 | 1. Prepared for sprint 1 presentation 2. Checked all the completed tasks of sprint 1 3. Summarize all the sprint 1 completed task
NewsAssistant | 2 | Developer | Chatbot functionality | Train chatbot to suggest news articles | Train chatbot on more databases
NewsAssistant | 2 | Developer | UI Pages development | Dynamic page and content | Add dynamic content - news from RSS feeds
NewsAssistant | 2 | Developer | Sprint 2 Presentation | Creating the presentation for sprint 2
NewsAssistant | 3 | Developer | UI Pages development | Improve homepage UI | Rework UI
NewsAssistant | 3 | Developer | Change chatbot backend | Improve chatbot functionality | Improve chatbot business logic
NewsAssistant | 3 | Developer | Add News source | Add functionality to fetch latest news | Fetch and display news content from NewsAPI.org
NewsAssistant | 3 | Developer | Chatbot Custom Actions | Train chatbot to respond based on user query | Code function for chatbot to fetch and provide user requested content
NewsAssistant | 3 | Developer | Sprint 3 Presentation | Creating the presentation for sprint 3