## Sheet 1 - Product Backlog
Product Backlog
Overall Project estimates
| Work estimate for sprint 1 (hrs) | 80
| Work estimate for sprint 2 (hrs) | 80
| Work estimate for sprint 3 (hrs) | 80
| Work estimate for sprint 4 (hrs) | 80
Sprint Information
| Current sprint | 1
| Total available days for the sprint | 10
| Resources available | 5
Application | Sprint | User role | User story | Details | Tasks
NewsAssistant | 1 | Developer | Chatbot functionality | Add funcitionality to chatbot so that it can train itself and provide more information
NewsAssistant | 1 | Developer | UI Pages development | Improve the overall UI of the web application | 1. Redesigned the login page & homepage
NewsAssistant | 1 | Developer | Sprint 1 Presentation | Creating the presentation for sprint 1 | 1. Prepared for sprint 1 presentation 2. Checked all the completed tasks of sprint 1 3. Summarize all the sprint 1 completed task
NewsAssistant | 2 | Developer | Chatbot functionality | Train chatbot to suggest news articles | Train chatbot on more databases
NewsAssistant | 2 | Developer | UI Pages development | Dynamic page and content | Add dynamic content - news from RSS feeds
NewsAssistant | 2 | Developer | Sprint 2 Presentation | Creating the presentation for sprint 2
NewsAssistant | 3 | Developer | UI Pages development | Improve homepage UI | Rework UI
NewsAssistant | 3 | Developer | Change chatbot backend | Improve chatbot functionality | Improve chatbot business logic
NewsAssistant | 3 | Developer | Add News source | Add functionality to fetch latest news | Fetch and display news content from NewsAPI.org
NewsAssistant | 3 | Developer | Chatbot Custom Actions | Train chatbot to respond based on user query | Code function for chatbot to fetch and provide user requested content
NewsAssistant | 3 | Developer | Sprint 3 Presentation | Creating the presentation for sprint 3
User Stories
| User Stories | Details | Sprints worked on | Sprint completed in | Status
| Interactive UI Pages | User should be easily able to traverse through the pages | Sprint 1,Sprint 2 | Sprint 2 | Complete
| User login | User should able to login with correct credetials | Sprint 1,Sprint 2 | Sprint 2 | Complete
| User authentication | User should not be able to login with invalid credentials | Sprint 1,Sprint 2 | Sprint 2 | Complete
| User sign up | user should be able to sign up after entering the details | Sprint 1 | Sprint 1 | Complete
| Database status | New user should be visible after a new sign up | Sprint 1 | Sprint 1 | Complete
| Forget password | User should be able to reset password from forget password link | Sprint 3, Sprint 4 | Sprint 4 | Complete
| Invalid password request | User should not be able to move forward if the email id is not found in the database | Sprint 3, Sprint 4 | Sprint 4 | Complete
| Sign out | User should be able to sign out and the sessio should be cleared | Sprint 4 | Sprint 4 | Complete
| News details | Top trending news should be visible to all the user without even log in | Sprint 3 | Sprint 3 | Complete
| News details on landing page | Top trending news should be visible to all the user after log in as well | Sprint 3 | Sprint 3 | Complete
| Categorised news display after login only | Once user is logged in he should be able to see the news category tab | Sprint 3 | Sprint 3 | Complete
| Chatbot UI appearance on all pages | The chatbot pop up should appear on all the pages | Sprint 3 | Sprint 3 | Complete
| Chatbot basic conversation | Chatbot should ne able to reply to greeting messages | Sprint 2, Sprint 3 | Sprint 3 | Complete
| Chatbot replying for a search keyword | Display the news related to the search keyword typed in the chatbot | Sprint 4 | Sprint 4 | Complete
| Deploying of the web application | Deploying the web application on heroku server | Sprint 4 | Sprint 4 | Complete
| Deploying of the chatbot backend | Deploying the chatbot backend to heroku server | Sprint 4 | Sprint 4 | Inprogress
| News preference | User should be able choose News preferences & topics of interest and save those preferences | Sprint 4 | Sprint 4 | Incomplete